## Project Information
PROJECT INFORMATION
Wind Farm/Project Name: | Start Date: | 2022-04-05
Address: | (Expected) Completion Date: | 2022-04-14
Company: | Company Performing Work: | 3S Americas, Inc.
Main Contact Name: | Total 3S System Type & Qty: | 99
Main Contact Title: | Tracker Updated: | 2022-04-14
Main Contact Phone Number: | Notes: | Annual Inspections and Repairs
Main Contact Email:

## 3S System Tracker
Tracker
WTG # | OEM/Model | Personnel Performing Inspection | Inspection Date | Retension Needed | Correction Needed | Notes | Estimated time to repair | Warranty item | Resolved
1 | GE | LUIS, DEVAN | 2022-04-05 | N
2 | GE | LUIS, DEVAN | 2022-04-05 | N |  | Replaced Left handle plastic,
3 | GE | LUIS, DEVAN | 2022-04-05 | N
4 | GE | LUIS, DEVAN | 2022-04-05 | N
5 | GE | LUIS, DEVAN | 2022-04-05 | N
6 | GE | LUIS, DEVAN | 2022-04-05 | N
7 | GE | LUIS, DEVAN | 2022-04-05 | N
8 | GE | LUIS, DEVAN | 2022-04-05 | N
9 | GE | LUIS, DEVAN | 2022-04-05 | N
10 | GE | LUIS, DEVAN | 2022-04-05 | Y |  | Car remote switch warning alarm not souding on. Corrected load cell wiring.
11 | GE | LUIS, DEVAN | 2022-04-05 | N
12 | GE | LUIS, DEVAN | 2022-04-05 | N
13 | GE | LUIS, DEVAN | 2022-04-06 | N
14 | GE | LUIS, DEVAN | 2022-04-06 | N
15 | GE | LUIS, DEVAN | 2022-04-06 | N
16 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Control box missing 1 screw (- Added 1 control box screw)
17 | GE | LUIS, DEVAN | 2022-04-06 | N
18 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Top cut rail missing 1 bracket (- Added 1 rung clamp)
19 | GE | LUIS, DEVAN | 2022-04-06 | N
20 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Traction unit cover damaged on left side (New traction unit cover)
21 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Traction unit cover damaged on Right side & 3rd deck guide roller missing 1 wheel (New traction unit cover - Added wheel & hardware on short guide pulley assembly)
22 | GE | LUIS, DEVAN | 2022-04-06 | N |  | 3rd deck guide roller missing 1 wheel & 4th deck guide roller missing 2 screws hardware. Corrected load cell wiring.
23 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Control box missing 2 screws (- Added 2 control box screw)
24 | GE | LUIS, DEVAN | 2022-04-06 | N
25 | GE | LUIS, DEVAN | 2022-04-06 | N
26 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Control box missing 2 screws (- Added 2 control box screw)
27 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Control box missing 1 screws & up switch functionality wont work.( New Receiver Board - New Emitter PCB inside the car - Cross swap handrail cable number 35 and 32)
28 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Traction unit cover missing 1 screw (- Added 1 traction unit cover screw.)
29 | GE | LUIS, DEVAN | 2022-04-06 | N
30 | GE | LUIS, DEVAN | 2022-04-06 | N |  | Control box missing 2 screws & top cut rail missing 2 brackets (- Added 2 control box screws - Added 2 rail rung clamps)
31 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Car, control box, & hand remote functionality doesn’t work (New receiver board - New Emitter PCB inside the car 9 digit - Cross swap handrail cable number 35 and 32)
32 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Missing car left side antenna (- New car antenna)
33 | GE | LUIS, DEVAN | 2022-04-07 | N
34 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Traction unit arm support missing 1 screw (- Added 1 screw for traction unit support bracket)
35 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Leaking in traction unit heat sink (Tighted oild plug behind the heat sink)
36 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Traction unit cover missing 1 screw (- Added 1 traction unit cover screw)
37 | GE | LUIS, DEVAN | 2022-04-07 | Y |  | Leaking in traction unit heat sink & control box missing 1 screw (- Added 1 control box screw - Tightened oil plug behind traction unit heat sink)
38 | GE | LUIS, DEVAN | 2022-04-07 | N
39 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Traction unit cover missing 1 screw & control box missing 1 screw (Added 1 traction unit cover screw - Added 1 control box screw)
40 | GE | LUIS, DEVAN | 2022-04-07 | Y
41 | GE | LUIS, DEVAN | 2022-04-07 | N
42 | GE | LUIS, DEVAN | 2022-04-07 | N
43 | GE | LUIS, DEVAN | 2022-04-07 | N |  | Traction unit cover damaged on left side & missing 1 screw (- New traction unit cover - Added 1 traction unit cover screw)
44 | GE | LUIS, DEVAN | 2022-04-07 | Y |  | Missing u-bolt spacers inside car (- Added 2 u-bolt spacers inside car)
45 | GE | LUIS, DEVAN | 2022-04-07 | N
46 | GE | LUIS, DEVAN | 2022-04-08 | Y |  | Guide roller missing screw & silver metal (Added metal tube with hardware to the short guide pulley assembly)
47 | GE | LUIS, DEVAN | 2022-04-08 | N
48 | GE | LUIS, DEVAN | 2022-04-08 | Y |  | Car left handle cover broken (New car left handrail)
49 | GE | LUIS, DEVAN | 2022-04-08 | N
50 | GE | LUIS, DEVAN | 2022-04-08 | N |  | Control box & hand remote settings didn’t work on 2nd attempt ( New receiver board - New Emitter PCB inside the car - Cross swap handrail cable number 35 and 32)
51 | GE | LUIS, DEVAN | 2022-04-08 | Y
52 | GE | LUIS, DEVAN | 2022-04-08 | Y
53 | GE | LUIS, DEVAN | 2022-04-08 | N
54 | GE | LUIS, DEVAN | 2022-04-08 | Y
55 | GE | LUIS, DEVAN | 2022-04-08 | N |  | Control box missing 4 screws (- Added 4 control box screw)
56 | GE | LUIS, DEVAN | 2022-04-08 | Y
57 | GE | LUIS, DEVAN | 2022-04-08 | N |  | Control box missing 1 screw (- Added 1 control box screw)
58 | GE | LUIS, DEVAN | 2022-04-08 | N |  | Traction unit cover missing 1 screw & Car E-stop button missing (- Added 1 traction unit cover screw - New E-stop car push button)
59 | GE | LUIS, DEVAN | 2022-04-08 | Y
60 | GE | LUIS, DEVAN | 2022-04-08 | Y
61 | GE | LUIS, DEVAN | 2022-04-08 | N
62 | GE | LUIS, DEVAN | 2022-04-08 | Y
63 | GE | LUIS, DEVAN | 2022-04-09 | N
64 | GE | LUIS, DEVAN | 2022-04-09 | N
65 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Traction unit cover damage & missing 1 screw.(- New traction unit cover - Added 1 traction unit cover screw)
66 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Control box missing 1 screw.(- Added 1 control box screw)
67 | GE | LUIS, DEVAN | 2022-04-09 | Y
68 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Control box missing 1 scew (- Added 1 control box screw)
69 | GE | LUIS, DEVAN | 2022-04-09 | N |  | Control box remote doesn’t work. Car remote alarm doenst work.(- Added 1 traction unit cover srew - New Receiver Board - New Emitter PCB inside the car - Cross swap handrail cables number 35 and 32)
70 | GE | LUIS, DEVAN | 2022-04-09 | N |  | Leak on traction unit heat sink & control box missing 2 screws.( Added 2 control box screw - Tighten oil plug behind traction unit sink)
71 | GE | LUIS, DEVAN | 2022-04-09 | N
72 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Guide pulley missing 1 wheel and hardware.(- Added 1 guide pulley wheel and hardware)
73 | GE | LUIS, DEVAN | 2022-04-09 | N |  | Control box missing 1 screw & car side anttenna missing ( - Added 1 control box screw - New car anttenna)
74 | GE | LUIS, DEVAN | 2022-04-09 | N
75 | GE | LUIS, DEVAN | 2022-04-09 | N |  | Control box missing 1 screw (- Added 1 control box screw)
76 | GE | LUIS, DEVAN | 2022-04-09 | N |  | Control box missing 1 screw & Leak on traction unit heat sink (- Added 1 control box screw - Tightened oil plug behind traction unit heat sink)
77 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Control box missing 1 screw & Leak on traction unit heat sink (- Added 1 control box screw- Tightened oil plug behind traction unit heat sink)
78 | GE | LUIS, DEVAN | 2022-04-09 | N
79 | GE | LUIS, DEVAN | 2022-04-09 | N
80 | GE | LUIS, DEVAN | 2022-04-09 | N
81 | GE | LUIS, DEVAN | 2022-04-09 | Y |  | Control box missing 1 screw (- Added 1 control box screw)
82 | GE | LUIS, DEVAN | 2022-04-11 | Y |  | Leak on traction unit heat sink ( - tightened oil plug behind traction unit heat sink)
83 | GE | LUIS, DEVAN | 2022-04-11 | Y
84 | GE | LUIS, DEVAN | 2022-04-11 | Y
85 | GE | LUIS, DEVAN | 2022-04-11 | Y
86 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Missing 1 rung clamp (- Added 1 rung clamp)
87 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Leak on traction unit heat sink (Tightened oild pulg behind the heat sink)
88 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Control box missing 1 screw (- Added 1 control box screw)
89 | GE | LUIS, DEVAN | 2022-04-11 | N
90 | GE | LUIS, DEVAN | 2022-04-11 | N
91 | GE | LUIS, DEVAN | 2022-04-11 | Y |  | Missing 1 rung clamp (- Added 1 rung clamp)
92 | GE | LUIS, DEVAN | 2022-04-11 | Y |  | Traction unit cover damaged left & right. Leak on traction unit heat sink (- Tightened oil plug behind traction unit heat sink - New 2 traction unit covers)
93 | GE | LUIS, DEVAN | 2022-04-11 | Y
94 | GE | LUIS, DEVAN | 2022-04-11 | Y
95 | GE | LUIS, DEVAN | 2022-04-11 | N
96 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Missing 1 speed flag (- Added 1 speed flag)
97 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Traction unit cover missing 1 screw and battery holder damaged (- Added 1 traction unit cover screw and replaced battery holder)
98 | GE | LUIS, DEVAN | 2022-04-11 | Y |  | Leak on traction unit heat sink & control box missing 1 screw (- Added 1 control box screw - Tightened oil plug behind traction unit heat sink)
99 | GE | LUIS, DEVAN | 2022-04-11 | N |  | Leak on traction unit heat sink (Tightened oil plug behind the heat sink)